## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | M-1 | 1.Choose the data (refer to Day 3 ppt) either small, medium or large text data. 2.Read the data file (either web scrap or import as csv or txt files) 3.Store the data in the database and fetch the data. 4. Do text cleaning(like removing unnecessary text like emojis) and Normalization (like lowercasing, tokenizing, lemmatizing , POS tagging) 5.Using multiprocessing techniques, find the word and its counts. | MUST HAVE
2 | 2 | M-2 | 1. Sentiment analysis / Text Classification / Topic modeling 2. Store in DB 3. Apply parallelism 4. Send the summary email | MUST HAVE
3 | 3 | M-3 | 1. Load Dataset. 2. Sends each data text in parallel to an LLM or any unsupervised learning algorithm for sentiment classification/topic modelling/text classification. 3. Saves results into a CSV (or your text storage DB). 4. Mail the CSV file. 5. Measure the accuracy and performance of output using traditional method / unsupervised learning method (measuring the output prediction time). | MUST HAVE
4 | 4 | M-4 | Create an UI part for your project.(preferably using streamlit) | MUST HAVE
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 20 | 13 | 2.5 | 2 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
M-1 | T-1 | Choose the data - either small, medium or large text data. | 2025-09-10 | 2025-09-10 | Muskan Soni | Analysis | Completed | 1 | bar: Day 1
M-1 | T-2 | Read dataset (via web scraping or CSV/TXT import) | 2025-09-11 | 2025-09-11 | Muskan Soni | Coding | Completed | 0.5 | Day 1: 0.5
M-1 | T-3 | Store dataset in database and fetch the data | 12 spt 2025 | 2025-09-12 | Muskan Soni | Coding | Completed | 0.5 | Day 1: 0.5
M-1 | T-4 | Do text cleaning(like removing unnecessary text like emojis) and Normalization (like lowercasing, tokenizing, lemmatizing , POS tagging) | 2025-09-15 | 2025-09-16 | Muskan Soni | Coding | Completed | 2 | bar: Day 1 to Day 2
M-1 | T-5 | Apply multiprocessing to count words and visualize | 2025-09-17 | 2025-09-17 | Muskan Soni | Coding | Completed | 1 | bar: Day 1
M-2 | T-1 | Sentiment analysis / Text Classification / Topic modeling | 2025-09-23 | 2025-09-24 | Muskan Soni | Coding | Completed | 0.5 | Day 1: 0.5
M-2 | T-2 | Store in DB | 2025-09-25 | 2025-09-25 | Muskan Soni | Coding | Completed | 0.5 | Day 1: 0.5
M-2 | T-3 | Apply parallelism | 2025-09-26 | 2025-09-26 | Muskan Soni | Coding | Completed | 1 | bar: Day 1
M-2 | T-4 | Send email summary | 2025-09-29 | 2025-09-29 | Muskan Soni | Coding | Completed | 1 | bar: Day 1
M-3 | T-1 | Integrate data loading and preprocessing into a single automated script | 2025-10-07 | 2025-10-07 | Muskan Soni | Coding | Completed | 1 | bar: Day 1
M-3 | T-2 | Implement parallel data sending to LLM / unsupervised model for sentiment analysis using modern technique | 2025-10-08 | 2025-10-10 | Muskan Soni | Coding | Completed | 3 | bar: Day 1 to Day 3
M-3 | T-3 | Save model predictions into CSV/DB | 2025-10-13 | 2025-10-13 | Muskan Soni | Coding | Completed | 0.5 | Day 1: 0.5
M-3 | T-4 | Automate email sending with processed CSV as attachment | 2025-10-14 | 2025-10-14 | Muskan Soni | Coding | Completed | 0.5 | Day 1: 0.5
M-3 | T-5 | Measure the accuracy and performance of output using traditional method / unsupervised learning method (measuring the output prediction time) | 2025-10-15 | 2025-10-15 | Muskan Soni | Coding | Completed | 2 | Day 1: 2
M-4 | T-1 | Build UI using Streamlit | 2025-10-16 | 2025-10-30 | Muskan Soni | Coding | Completed | 5 | Day 1: 1; Day 2: 0.5; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 0.5
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 2025-09-08 | Overview of project | Got to know about the parallel text processing
1 | 2025-09-09 | Serial vs Parallel Processing | understood the working by implementing the code
1 | 2025-09-10 | Sqlite3 built in database introduction | worked with sqlite3 database
1 | 2025-09-11 | Regular Expression concept | learned regex concepts
1 | 2025-09-12 | Dataset Selection guidance, exploration | chose a small text data base(tweets), loaded the database and explored it
1 | 2025-09-15 | Dataset storing and preprocessing | store the data in database and fetched the data, done text cleaning and normalization
1 | 2025-09-16 | Apply multiprocessing techniques on chosen dataset | aaplied multiprocessing techniques and found the most common word
1 | 2025-09-17 | Milestone-1 presentations | presented my work for milestone-1
2 | 2025-09-18 | Discussed about problem statements(sentiment analysis, topic modeling, text classification | understood the problem statements significance and relevance to my chosen dataset
2 | 2025-09-24 | Email sending procecude | worked on email sending concepts by using smtplib, email libraries of python
2 | 2025-09-26 | Problem statement finalization | chose sentiment analysis as my problem statement and researched about its working
2 | 2025-10-03 | Milestone-2 presentations | completed the remaining tasks of milestone-2
2 | 2025-10-04 | Milestone-2 presentations | presented my work for milestone-2
3 | 2025-10-06 | Uploaded Milestone-2 and discussed Milestone-3 goals | understood the goals for milestone-3
3 | 2025-10-07 | Explained the tasks of milestone 3 and started implemneting | started working for milestone-3
3 | 2025-10-09 | Explained about performance, accuracy and time comparision metrics | Researched about the performance metrics for the project
3 | 2025-10-10 | Explained sentiment analysis using a modern technique | Reseached about the modern techniques
3 | 2025-10-11 | Do sentiment analysis usign parallel processing and LLM | Implemented a Hugging Face model for sentiment anaylsis
3 | 2025-10-13 | Record the time and performance for both techiniques | Implemented time and performance metrics
3 | 2025-10-14 | Analyse which method works better | Analysis of both traditional and modern method
3 | 2025-10-15 | Milestone-3 presentations | presented my work for milestone-2
4 | 2025-10-16 | Introduced to streamlit | explored streamlit to build UI for the project
4 | 2025-10-17 | Explained the tasks for milestone-4 | understood the tasks and goals for milestone-4
4 | 2025-10-23 | start developing UI for the project | Started working on streamlit
4 | 2025-10-24 | Develop the file upload, preprocess and word count pages | Developed UI pages for filrupload, preprocess and word count
4 | 2025-10-27 | Make sentiment anaysis page | Implamented UI fro sentiment analysis page
4 | 2025-10-28 | Develop other pages like downlaod, email, login pages | Added more features
4 | 2025-10-30 | Milestone-4 presentation | Presented my work for milestone-4
4 | 2025-10-04 | Mock presentations | Mock presentations
4

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-08 | 2025-09-17 | Muskan Soni | Choosing dataset, Reading data, Storing & fetching from DB | Choosing dataset (once finalized, no longer needed) | Text cleaning, Normalization, Word count with multiprocessing | Dataset finalized (small), stored in DB, cleaning and normalization continued
2 | 2 | 2025-09-24 | 2025-10-04 | Muskan Soni | Sentiment analysis, Applying parallelism, Sending summary email | Word count task (from Sprint 1, completed) | Storing processed results in DB, Running sentiment analysis | Implemented sentiment analysis model, stored results, automated summary email
3 | 3 | 2025-10-06 | 2025-10-17 | Muskan Soni | Loading full dataset, Sending data to LLM/unsupervised model for sentiment/topic classification, Measuring accuracy and performance | Manual testing of sentiment outputs | Storing processed results into DB/CSV, Emailing final CSV report | Implemented automated LLM/unsupervised processing pipeline, measured runtime performance, and mailed final CSV results
4 | 4 | 2025-10-17 |  | Muskan Soni | Creating Streamlit UI for visualization and interaction, Integrating backend with UI | Manual data inspection and local CSV verification | Displaying processed results, Metrics visualization, Email CSV integration | Developed Streamlit-based UI to upload data, view sentiment results, visualize metrics, and download CSV output